## Dashboard
KẾ HOẠCH VÀ TIẾN ĐỘ CÔNG VIỆC
PROJECT TITLE |  | 04. Phát triển hệ thống hỗ trợ quản lý chuỗi cung ứng hàng hóa |  |  |  |  | COMPANY NAME
PROJECT MANAGER |  | NGUYỄN TRỊNH ĐÔNG |  |  |  |  | DATE
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | DANH MỤC CÁC CÔNG VIỆC | [10 empty] | 23/9 | 24 | 25 | 26 | 27 | 30 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20
STB-1 | Common Components |  | 2024-09-20 | 2024-10-01
STB-2 | Common Web Components - Icons | LLDT | 2024-09-22 | 2024-10-01 | 5 | 100%
STB-3 | Common Web Components - Typography | VHQA | 2024-09-22 | 2024-10-01 | 3 | 100% | bar: WEEK 2 M 23/9 to WEEK 2 W 25
STB-4 | Common Web Components - Icon Button | NTNH | 2024-09-22 | 2024-10-01 | 2 | 100% | bar: WEEK 2 M 23/9 to WEEK 2 T 24
STB-5 | Common Web Components - Button | GBA | 2024-09-22 | 2024-10-01 | 4 | 100% | bar: WEEK 2 M 23/9 to WEEK 2 R 26
STB-10 | Partner Management
STB-6 | Create Partners |  | 30/09/24 | 15/10/24 |  | 98% | bar: WEEK 4 M 7 to WEEK 4 R 10
STB-12 | Create Partners-BE | LLDT | 30/09/24 | 15/10/24 | 10 | 100% | bar: WEEK 3 T 1 to WEEK 4 F 11
STB-22 | Create Partners- Integrate FE with BE's API | LLDT | 30/09/24 | 15/10/24 | 12 | 90% | bar: WEEK 3 F 4 to WEEK 4 F 11
STB-25 | Create Partners-Test case | DHH | 30/09/24 | 15/10/24 | 10 | 100% | bar: WEEK 3 F 4 to WEEK 4 F 11
STB-11 | Create Partners-FE | NTNH | 30/09/24 | 15/10/24 | 10 | 100% | bar: WEEK 3 W 2 to WEEK 4 F 11
STB-26 | Sidebar | NTNH | 30/09/24 | 15/10/24 | 9 | 100% | bar: WEEK 3 F 4 to WEEK 4 R 10
STB-7 | Edit Partner |  | 30/09/24 | 15/10/24 |  | 95%
STB-13 | Edit Partner - FE | GBA | 30/09/24 | 15/10/24 | 10 | 100% | bar: WEEK 3 F 4 to WEEK 4 F 11
STB-23 | Edit Partner - BE | LLDT | 30/09/24 | 15/10/24 | 12 | 90%
STB-24 | Edit Partner - Integrate FE with BE's API | LLDT | 30/09/24 | 15/10/24 | 10 | 100% | bar: WEEK 3 F 4 to WEEK 4 F 11
STB-26 | Edit Partner - Test case | DHH | 30/09/24 | 15/10/24 | 10 | 100% | bar: WEEK 3 F 4 to WEEK 4 F 11
STB-9 | List Partner |  | 30/09/24 | 15/10/24 |  | 100%
STB-17 | List Partner - FE | VHQA | 30/09/24 | 15/10/24 | 10 | 100% | bar: WEEK 3 F 4 to WEEK 4 F 11
STB-20 | List Partner - Test case | DHH | 30/09/24 | 15/10/24 | 10 | 100% | bar: WEEK 3 F 4 to WEEK 4 F 11
STB-8 | List Partner |  |  |  |  | 100%
STB-15 | List Partner - FE | GBA | 30/09/24 | 15/10/24 | 10 | 100% | bar: WEEK 3 F 4 to WEEK 4 F 11
STB-27 | List Partner - Test case | DHH | 30/09/24 | 15/10/24 | 5 | 100%
STB-30 | Activity diagram for Partner Management | TLYL | 30/09/24 | 15/10/24 | 9 | 100% | bar: WEEK 4 M 7 to WEEK 5 T 15
STB-36 | Usecase diagram for Partner Management | VHQA | 30/09/24 | 15/10/24 | 9 | 100% | bar: WEEK 4 M 7 to WEEK 5 T 15
STB-35 | Sequence diagram for Partner Management | GBA | 30/09/24 | 15/10/24 | 9 | 100% | bar: WEEK 4 M 7 to WEEK 5 T 15
STB-31 | Warehouse Management
STB-37 | Activity diagram for Warehouse Management | TLYL | 16/10/24 | 2024-01-11 | 9 | 100% | bar: WEEK 5 W 16 to WEEK 6 F 25
STB-38 | Sequence diagram for Warehouse Management | NTNH | 16/10/24 | 2024-01-11 | 9 | 100% | bar: WEEK 5 F 18 to WEEK 7 T 30
STB-39 | Usecase diagram for Warehouse Management | LLDT | 16/10/24 | 2024-01-11 | 9 | 100% | bar: WEEK 5 R 17 to WEEK 7 M 29
STB-43 | Orders Management
STB-40 | Activity diagram for Orders Management | VHQA | 2024-11-02 | 2024-11-16 | 10 | 100% | bar: WEEK 7 F 2 to WEEK 9 T 13
STB-41 | Sequence diagram for Orders Management | NTNH | 2024-11-02 | 2024-11-16 | 10 | 100% | bar: WEEK 8 T 6 to WEEK 9 R 15
STB-42 | Usecase diagram for Orders Management | LLDT | 2024-11-02 | 2024-11-16 | 10 | 100% | bar: WEEK 8 M 5 to WEEK 9 W 14
STB-44 | Shipment Management
STB-45 | Activity diagram for Shipment Management | VHQA | 2024-11-02 | 2024-11-16 | 10 | 100% | bar: WEEK 7 F 2 to WEEK 9 T 13
STB-46 | Sequence diagram for Shipment Management | GBA | 2024-11-02 | 2024-11-16 | 10 | 100% | bar: WEEK 8 T 6 to WEEK 9 R 15
STB-47 | Usecase diagram for Shipment Management | LLDT | 2024-11-02 | 2024-11-16 | 10 | 100% | bar: WEEK 8 M 5 to WEEK 9 W 14
STB-51 | Shipment Management
STB-48 | Activity diagram for Shipment Management | TLYL | 2024-11-02 | 2024-11-16 | 10 | 100% | bar: WEEK 8 T 6 to WEEK 9 R 15
STB-49 | Sequence diagram for Shipment Management | TLYL | 2024-11-02 | 2024-11-16 | 10 | 100% | bar: WEEK 8 T 6 to WEEK 9 R 15
STB-50 | Usecase diagram for Shipment Management | TLYL | 2024-11-02 | 2024-11-16 | 10 | 100% | bar: WEEK 8 T 6 to WEEK 9 R 15
STB-52 | Driver Management
STB-70 | Create Driver - FE | VHQA | 18/11/24 | 2024-12-04 | 12 | 100% | bar: WEEK 10 M 19 to WEEK 12 M 2
STB-56 | Create Driver - Testcase | DHH | 18/11/24 | 2024-12-04 | 12 | 95% | bar: WEEK 10 T 20 to WEEK 12 T 3
STB-62 | List Driver - FE | GBA | 18/11/24 | 2024-12-04 | 12 | 100% | bar: WEEK 10 M 19 to WEEK 12 M 2
STB-64 | List Driver - Testcase | DHH | 18/11/24 | 2024-12-04 | 12 | 100% | bar: WEEK 10 T 20 to WEEK 12 T 3
STB-78 | Edit Driver - FE | NTNH | 18/11/24 | 2024-12-04 | 12 | 100% | bar: WEEK 10 M 19 to WEEK 12 M 2
STB-80 | Edit Driver - Testcase | DHH | 18/11/24 | 2024-12-04 | 12 | 95% | bar: WEEK 10 T 20 to WEEK 12 T 3
STB-86 | Delete Driver - FE | LLDT | 18/11/24 | 2024-12-04 | 12 | 100% | bar: WEEK 10 M 19 to WEEK 12 M 2
STB-88 | Delete Driver - Testcase | DHH | 18/11/24 | 2024-12-04 | 12 | 90% | bar: WEEK 10 T 20 to WEEK 12 T 3
STB-90 | Draw WireFrame
STB-91 | List Import order , export order | GBA | 2024-04-12 | 18/12/24 | 10 | 100%
STB-92 | Form Create Import, Export | VHQA | 2024-04-12 | 18/12/24 | 10 | 100% | bar: WEEK 12 R 5 to WEEK 12 M 16
STB-93 | Form Confirm Import, Export | LLDT | 2024-04-12 | 18/12/24 | 10 | 100% | bar: WEEK 12 F 6 to WEEK 12 T 17
STB-94 | Form Create Shipment | NTNH | 2024-04-12 | 18/12/24 | 10 | 100% | bar: WEEK 12 F 6 to WEEK 12 T 17
Slide
2 | Project Definition and Planning
2.1 |  |  | 2024-03-24 | 2024-03-28 | 4 | 22% | bar: WEEK 11 M 9 to WEEK 11 F 13
2.2 |  |  | 2024-03-29 | 2024-04-02 | 3 | 16% | bar: WEEK 11 M 9 to WEEK 11 F 13
2.3 |  |  |  |  | 0 | 0% | bar: WEEK 11 M 9 to WEEK 11 F 13
2.4 |  |  |  |  | 0 | 0% | bar: WEEK 11 M 9 to WEEK 11 F 13
3 | Project Conception and Initiation
3.1 |  |  |  |  | 0 | 0% | bar: WEEK 11 M 9 to WEEK 11 F 13
3.2 |  |  |  |  | 0 | 0% | bar: WEEK 11 M 9 to WEEK 11 F 13
3.2.1 |  |  |  |  | 0 | 0% | bar: WEEK 11 M 9 to WEEK 11 F 13
3.2.2 |  |  |  |  | 0 | 0% | bar: WEEK 11 M 9 to WEEK 11 F 13
3.3 |  |  |  |  | 0 | 0% | bar: WEEK 11 M 9 to WEEK 11 F 13
3.3.1 |  |  |  |  | 0 | 0% | bar: WEEK 11 M 9 to WEEK 11 F 13
4 | Project Performance / Monitoring
4.1 |  |  |  |  | 0 | 0%
4.2 |  |  |  |  | 0 | 0%
4.3 |  |  |  |  | 0 | 0%
4.4 |  |  |  |  | 0 | 0%

## Chi tiết các công việc
DANH MỤC CHI TIẾT CÁC CÔNG VIỆC
Stt | Tên công việc chính | Trạng thái công việc
|  | Khởi động | Đang làm | Hoàn thành