## Dashboard
KẾ HOẠCH VÀ TIẾN ĐỘ CÔNG VIỆC
PROJECT TITLE |  | 04. Phát triển hệ thống hỗ trợ quản lý chuỗi cung ứng hàng hóa |  |  |  |  | COMPANY NAME | [6 empty] | Team 4 - Team C
PROJECT MANAGER |  | NGUYỄN TRỊNH ĐÔNG |  |  |  |  | DATE | [6 empty] | 15/09/2024
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
I | Common Mobile Components |  | 2024-09-21 | 2024-10-01 | 10 | 100%
1 | Common Mobile Components -Color | TS | 2024-09-21 | 2024-10-01 | 10 | 100% | bar: WEEK 2 M to WEEK 3 T; WEEK 11 M to WEEK 11 T
2 | Common Mobile Components - Icon | NTT | 2024-09-22 | 2024-10-01 | 9 | 100% | bar: WEEK 2 M to WEEK 3 T; WEEK 11 M to WEEK 11 T
3 | Common Mobile Components - Text Area | TS | 2024-09-22 | 2024-10-01 | 9 | 100% | bar: WEEK 2 M to WEEK 3 T; WEEK 11 M to WEEK 11 T
4 | Common Mobile Components - Typography | VH | 2024-09-22 | 2024-10-01 | 9 | 100% | bar: WEEK 2 M to WEEK 3 T; WEEK 11 M to WEEK 11 T
5 | Common Mobile Components - Input Field | NTT | 2024-09-22 | 2024-10-01 | 9 | 100% | bar: WEEK 2 M to WEEK 3 T; WEEK 11 M to WEEK 11 T
II | Create Product |  | 2024-10-02 |  | 0 | 66.67%
1 | Create Product - FE UI | TS | 2024-10-02 | 2024-10-14 | 12 | 100% | bar: WEEK 3 W to WEEK 5 F; WEEK 11 M to WEEK 11 T
2 | Create Product - BE | PNQ | 2024-10-14 | 2024-10-17 | 3 | 100% | bar: WEEK 11 M to WEEK 11 T
3 | Create Product - Integrate FE with API BE | NTT | 2024-10-02 |  | 0 | 0% | bar: WEEK 11 M to WEEK 11 T
III | Edit Product |  | 2024-10-02 |  | 0 | 66.67%
1 | Edit Product - FE UI | TS | 2024-10-02 | 2024-10-14 | 12 | 100% | bar: WEEK 3 W to WEEK 5 F; WEEK 11 M to WEEK 11 T
2 | Edit Product - BE | PNQ | 2024-10-14 | 2024-10-17 | 3 | 100% | bar: WEEK 11 M to WEEK 11 T
3 | Edit Product - Integrate FE with API BE | TS | 2024-10-02 |  | 0 | 0% | bar: WEEK 11 M to WEEK 11 T
IV | Delete Product |  | 2024-10-02 |  | 0 | 66.67%
1 | Delete Product- FE UI | TS | 2024-10-02 | 2024-10-14 | 12 | 100% | bar: WEEK 3 W to WEEK 5 F; WEEK 11 M to WEEK 11 T
2 | Delete Product - BE | PNQ | 2024-10-14 | 2024-10-17 | 3 | 100% | bar: WEEK 11 M to WEEK 11 T
3 | Delete Product - Integrate FE with API BE | TS | 2024-10-02 |  | 0 | 0% | bar: WEEK 11 M to WEEK 11 T
V | View Product List |  | 2024-10-02 |  | 0 | 66.67%
1 | View Product List- FE UI | NTT | 2024-10-02 | 2024-10-14 | 12 | 100% | bar: WEEK 3 W to WEEK 5 F; WEEK 11 M to WEEK 11 T
2 | View Product List - BE | PNQ | 2024-10-14 | 2024-10-17 | 3 | 100% | bar: WEEK 11 M to WEEK 11 T
3 | View Product List - Integrate FE with API BE | NTT | 2024-10-02 |  | 0 | 0% | bar: WEEK 11 M to WEEK 11 T
VI | Diagram for Partner Management |  | 2024-10-16 | 2024-10-24 | 8 | 100%
1 | Partner Management - Sequence Diagram | NTT | 2024-10-16 | 2024-10-17 | 1 | 100% | bar: WEEK 11 M to WEEK 11 T
2 | Partner Management - Activity Diagram | TS | 2024-10-16 | 2024-10-19 | 3 | 100% | bar: WEEK 11 M to WEEK 11 T
3 | Partner Management - Usecase Diagram | PNQ | 2024-10-16 | 2024-10-24 | 8 | 100% | bar: WEEK 5 M to WEEK 6 R; WEEK 11 M to WEEK 11 T
VII | Other Diagram |  |  |  |  | 100%
1 | ERD | PNMK | 2024-10-16 | 2024-10-20 | 4 | 100% | bar: WEEK 11 M to WEEK 11 T
2 | DB Schema | PNMK | 2024-10-16 | 2024-10-20 | 4 | 100% | bar: WEEK 11 M to WEEK 11 T
3 | Class Diagram | PNMK | 2024-10-16 | 2024-10-20 | 4 | 100% | bar: WEEK 11 M to WEEK 11 T
VIII | Diagram for Vehicle/Driver Management |  | 2024-10-24 | 2024-11-02 | 8 | 100%
1 | Sequence Diagram | NTT | 2024-10-24 | 2024-10-31 | 7 | 100% | bar: WEEK 6 R to WEEK 7 R; WEEK 11 M to WEEK 11 T
2 | Activity Diagram | TS | 2024-10-24 | 2024-11-02 | 8 | 100% | bar: WEEK 6 R to WEEK 7 F; WEEK 11 M to WEEK 11 T
3 | Usecase Diagram | PNQ | 2024-10-24 | 2024-11-01 | 7 | 100% | bar: WEEK 6 R to WEEK 7 F; WEEK 11 M to WEEK 11 T
IX | Mid-term Report |  | 2024-11-01 | 2024-11-07 | 6 | 100%
1 | List Description | PNMK | 2024-11-01 | 2024-11-07 | 6 | 100% | bar: WEEK 7 F to WEEK 8 R
X | Mobile UI 1 |  | 2024-11-19 | 2024-11-26 | 7 | 100%
1 | Partner Management - Form | TS | 2024-11-19 | 2024-11-26 | 7 | 100% | bar: WEEK 10 T to WEEK 11 T
2 | Partner Management - List | NTT | 2024-11-19 | 2024-11-26 | 7 | 100% | bar: WEEK 10 T to WEEK 11 T
3 | Legal Person Management - Form | TS | 2024-11-19 | 2024-11-26 | 7 | 100% | bar: WEEK 10 T to WEEK 11 T
4 | Legal Person Management - List | NTT | 2024-11-19 | 2024-12-03 | 14 | 100% | bar: WEEK 10 T to WEEK 12 T
XI | Mobile UI 2 |  | 2024-11-26 | 2024-12-08 | 12 | 100%
1 | Warehouse Management - Form | TS | 2024-11-26 | 2024-12-03 | 7 | 100% | bar: WEEK 11 M to WEEK 12 T
2 | Warehouse Management - List | NTT | 2024-11-26 | 2024-12-03 | 7 | 100% | bar: WEEK 11 M to WEEK 12 T
3 | Product Management - Form | TS | 2024-12-04 | 2024-12-09 | 5 | 100% | bar: WEEK 11 M to WEEK 11 T; WEEK 12 W to WEEK 13 M
4 | Product Management - List | NTT | 2024-12-04 | 2024-12-09 | 5 | 100% | bar: WEEK 11 M to WEEK 11 T; WEEK 12 W to WEEK 13 M
XII | Wireframe for Driver,Vehicle,Order Management |  | 2024-11-26 | 2024-12-08 | 12 | 100%
1 | Form - Createnew Page | TS | 2024-12-17 | 2024-12-18 | 1 | 100% | bar: WEEK 11 M to WEEK 11 T; WEEK 14 T to WEEK 14 W
2 | List - Manage Page | NTT | 2024-12-17 | 2024-12-18 | 1 | 100% | bar: WEEK 11 M to WEEK 11 T; WEEK 14 T to WEEK 14 W
3 | Receipt | PNQ | 2024-12-17 | 2024-12-18 | 1 | 100% | bar: WEEK 11 M to WEEK 11 T; WEEK 14 T to WEEK 14 W
4 |  |  |  |  | 0 | 100% | bar: WEEK 11 M to WEEK 11 T

## Chi tiết các công việc
DANH MỤC CHI TIẾT CÁC CÔNG VIỆC
Stt | Tên công việc chính | Trạng thái công việc
|  | Khởi động | Đang làm | Hoàn thành